## Slide 1: Optimising Developing Heart Growth Problem
Hashem Yousefi

## Slide 2: Outline
Update on work done in the previous week
Issues which are not resolved
Action items from the other aspects
Plans for the following week
Submitting to the EMAC proceeding

## Slide 3: Last Week
Checking other optimization methods (SNOPT, ALHSO) in the pyOpt Module
Plotting the objective function for a simple 2-D case …
Reading the mesh
Following up on a report for the Mesh Painting section
Notification of acceptance received from EMAC

## Slide 4: Problems tried many times on B.Cs. but all failed

## Slide 5: Forward Problem for 8 Elements to Test 12 Growth Rates with ALHSO
form of final answer
Fibre , sheet, normal
[0.0065, 0.025, 0.0001, 0.0045, 0.015, 0.0001, 0.0025, 0.005, 0.0001, 0.0045, 0.015, 0.0001]

## Slide 6: Optimisers
Name | SLSQP | NSGA2 | NSGA2 + SLSQP | NLPQLP & SNOPT | ALPSO | ALHSO | MIDACO
Problem | 1 Elements 2 Elements 8 Elements | 8 Elements20x20 8 Elements20x40 | 8 Elements (20Gen-20size) 8 Elements (20Gen-40size) | ------- | 1 Elements 2 Elements 8 Elements | 8 Elements-hms5 8 Elements-hms15 | 8 Elements
Time | 1-2 hours 1-2 hours 1-2 hours | 5 hours 11 hours | 6 hours 17 hours With not a good initial condition | -------- | 2hours 1.2 hrs ,2.5-5 hrs 72hrs, 10hrs, 6hrs, 20hrs | 8 hours 9 hours Both stopped before SLSQP | Stopped
Min Obj Value | 0.000064 0.17 0.29- 0.38-1.0 | 0.22 0.1 | 0.17 0.04 | -------- | 0.61 (size40) 0.19 (5),0.10(40) 0.85(10), 0.1 (15), 0.29(30), -(60) | 0.36 (500 calls) 0.17 (600 calls) | Answers are far away from what expected

## Slide 7: Next Week Plans
+ Reading the derivatives ,,, (checking if the mesh is fine)
+Trying to import a mesh two meshes and provide the differences of them as the objective
+ Writing a report for the pros and cons of the optimizers
+ Finding how to apply parallelisation
+ complete the report by Monday